## Sheet1
Sprint | Task | Subtask
Sprint 1 | Project Setup & Planning | Set up GitHub repo & branching strategy
Sprint 1 | Project Setup & Planning | Install Spring Boot + PostgreSQL + Redis
Sprint 1 | Project Setup & Planning | Initialize Rider & Captain Flutter projects
Sprint 1 | Project Setup & Planning | Setup CI/CD pipeline (GitHub Actions)
Sprint 2 | Backend Foundations | User service (Signup/Login APIs with JWT)
Sprint 2 | Backend Foundations | Database schema migrations
Sprint 2 | Backend Foundations | Dockerize backend services
Sprint 2 | Backend Foundations | Basic API documentation (Swagger/OpenAPI)
Sprint 3 | Mobile Foundations | Rider app: Signup/Login UI
Sprint 3 | Mobile Foundations | Captain app: Signup/Login UI
Sprint 3 | Mobile Foundations | Integrate APIs for authentication
Sprint 4 | Core Ride Flow (Part 1) | Trip request API (Rider → Backend)
Sprint 4 | Core Ride Flow (Part 1) | Captain availability API
Sprint 4 | Core Ride Flow (Part 1) | Assign nearest captain logic
Sprint 4 | Core Ride Flow (Part 1) | Rider app: Request ride screen
Sprint 5 | Core Ride Flow (Part 2) | Captain app: Accept/Reject trip
Sprint 5 | Core Ride Flow (Part 2) | Rider app: Show captain info & ETA
Sprint 5 | Core Ride Flow (Part 2) | Trip status updates (WebSocket)
Sprint 6 | Payments & Commission | Integrate Razorpay/Stripe sandbox
Sprint 6 | Payments & Commission | Ride fare calculation API
Sprint 6 | Payments & Commission | Flat ₹5 commission logic
Sprint 6 | Payments & Commission | Payment success/failure UI
Sprint 7 | Maps & Navigation | Integrate Google Maps SDK (Flutter)
Sprint 7 | Maps & Navigation | Backend support for distance calculation
Sprint 7 | Maps & Navigation | Captain app: Navigation screen
Sprint 8 | User Profiles & Ratings | Rider profile API + UI
Sprint 8 | User Profiles & Ratings | Captain profile API + UI
Sprint 8 | User Profiles & Ratings | Ratings & feedback system
Sprint 9 | Notifications | Push notifications (Firebase FCM)
Sprint 9 | Notifications | Trip request/response notifications
Sprint 9 | Notifications | Payment confirmation notifications
Sprint 10 | Admin Dashboard | React + Vite app setup
Sprint 10 | Admin Dashboard | Login for admins
Sprint 10 | Admin Dashboard | View rides, users, captains
Sprint 10 | Admin Dashboard | Basic reporting & analytics
Sprint 11 | Testing & Optimization | Unit tests for backend APIs
Sprint 11 | Testing & Optimization | Integration tests
Sprint 11 | Testing & Optimization | Flutter widget tests
Sprint 11 | Testing & Optimization | Load testing for ride flow
Sprint 12 | Deployment & Launch | Prepare AWS/DigitalOcean infra
Sprint 12 | Deployment & Launch | Deploy backend & database
Sprint 12 | Deployment & Launch | Publish Rider app (Play Store)
Sprint 12 | Deployment & Launch | Publish Captain app (Play Store)